## Project Settings
/Proyecto/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Kevin Ray Marzola Otero
Start Date | may 01, 2017 10:10:20 AM
Completion Date | may 02, 2017 06:10:50 AM | Completed: *
Keywords
Language | Java
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:04 PM el 2/05/2017

## Overall Metrics
/Proyecto/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 29.8 | 17.8 | 33.1
Planned Time | 0.20556 |  | 1899-12-31 16:20
Actual Tiempo |  | 0.20833 | 1899-12-31 12:57
CPI (Cost-Performance Index) |  |  | 1.09
% Reuse | 43.2% | 47.6% | 25.6%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 3.53 | 11.2 | 4.09
Total Defects/KLOC or equivalent | 17.7 | 78.7 | 22.1
Yield % | 100% | 85.7% | 95.7%
Code Review Rate | 477 | 254 | 520
% Appraisal COQ | 14.1% | 14.3% | 14.2%
% Failure COQ | 7.77% | 8.67% | 7.89%
COQ A/F Ratio | 1.82 | 1.65 | 1.79
PQI | 0.17 | 0.2 | 0.19
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:04 PM el 2/05/2017

## Program Size
/Proyecto/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Program Size
| Plan | Actual | A la Fecha
Base (B) | 282 | 282 | 978
Deleted (D) | 2 | 1 | 78
Modified (M) | 18 | 24 | 88
Added (A) | 129 | 65 | 1134
Reused (R) | 311 | 314 | 625
Added and Modified (A+M) | 147 | 89 | 1222
Total Size (T) | 720 | 660 | 2439
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 175 | 189 | 1123
Upper Prediction Interval (70%) | N/A
Lower Prediction Interval (70%) | N/A
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:05 PM el 2/05/2017

## Time In Phase
/Proyecto/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.047917 | 0.035417 | 0.34583 | 22.5%
DiseÃ±o | 0.027083 | 0.031944 | 0.20625 | 13.4%
RevisiÃ³n de DiseÃ±o | 0.015972 | 0.015278 | 0.12014 | 7.8%
CodificaciÃ³n | 0.063889 | 0.052083 | 0.46667 | 30.3%
RevisiÃ³n de CodificaciÃ³n | 0.013194 | 0.014583 | 0.097917 | 6.36%
CompilaciÃ³n | 0.0048611 | 0.0034722 | 0.036111 | 2.35%
Pruebas | 0.011111 | 0.014583 | 0.085417 | 5.55%
Postmortem | 0.021528 | 0.040972 | 0.18125 | 11.8%
Total | 0.20556 | 0.20833 | 1899-12-31 12:57
Total Time UPI (70%) | N/A
Total Time LPI (70%) | N/A
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:05 PM el 2/05/2017

## Defects Injected
/Proyecto/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0.26 | 0 | 2 | 7.41%
DiseÃ±o | 1.3 | 3 | 13 | 48.1%
RevisiÃ³n de DiseÃ±o | 0 | 1 | 1 | 3.7%
CodificaciÃ³n | 0.52 | 3 | 7 | 25.9%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0.52 | 0 | 4 | 14.8%
Total | 2.6 | 7 | 27
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:06 PM el 2/05/2017

## Defects Removed
/Proyecto/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.26 | 0 | 2 | 7.41%
DiseÃ±o | 0.26 | 1 | 3 | 11.1%
RevisiÃ³n de DiseÃ±o | 0.65 | 2 | 7 | 25.9%
CodificaciÃ³n | 0.39 | 1 | 4 | 14.8%
RevisiÃ³n de CodificaciÃ³n | 0.52 | 2 | 6 | 22.2%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0.52 | 1 | 5 | 18.5%
Total | 2.6 | 7 | 27
After Development | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:06 PM el 2/05/2017

## Defect Removal Efficiency
/Proyecto/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 1.67 | 5.45 | 2.43
Defects/Hour - Code Review | 1.68 | 5.71 | 2.55
Defects/Hour - Compile | 0 | 0 | 0
Defects/Hour - Test | 1.98 | 2.86 | 2.44
DRL (DLDR/UT) | 0.84 | 1.91 | 1
DRL (Code Review/UT) | 0.85 | 2 | 1.05
DRL (Compile/UT) | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:07 PM el 2/05/2017